## Sheet1
[6 empty] | Semester 1 | [47 empty] | Holidays | [27 empty] | Exam Period | [20 empty] | Semester 2
[5 empty] | week 9 | [6 empty] | week 10 | [6 empty] | week 11 | [6 empty] | week 12 | [6 empty] | week 13 | [6 empty] | week 14 | [6 empty] | week 15 | [6 empty] | Week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 4 | [6 empty] | week 1 | [6 empty] | week 2 | [6 empty] | week 3 | [6 empty] | week 1 | [6 empty] | week 2 | [6 empty] | HAND IN
|  | Task ID | Task Name | Related Tasks | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 1 | Begin PMW Development | bar: week 9 M to week 9 S
|  | 2 | Update PMW based on feedback | 1 | bar: week 10 M to week 13 W
|  | 3 | Update the Team Page | 2 | bar: week 10 M to week 10 T
Key |  | 4 | Keep Work Planned up to Date | 2
| Work done after deadline | 5 | Create forum | 2 | week 1 M: New Forum Created
| Expected Time Period | 6 | Begin work on Main Site
| Work done before deadline | 7 | Base work for Make a Booking | 6 | bar: Week 1 M to week 3 S
|  | 8 | Module information working | 7 | bar: Week 1 M to week 4 S
|  | 9 | Module information validated | 8 | bar: week 1 M to week 1 W
|  | 10 | Room information working | 7 | bar: Week 1 M to week 4 S
|  | 11 | Room information validated | 10 | bar: week 1 T to week 1 T
|  | 12 | Time information working | 7 | bar: Week 1 M to week 4 S
|  | 13 | Time information validated | 12 | bar: week 1 W to week 1 F
|  | 14 | Make a booking complete | 6 | bar: week 1 S to week 2 T
|  | 15 | Start Room information page | 6 | bar: week 14 T to week 3 M
|  | 16 | Create room select | 15 | bar: week 14 T to week 3 M
|  | 17 | Validate room select | 17 | bar: week 1 S to week 2 M
|  | 18 | Create room profile | 15 | bar: week 14 T to week 3 M
|  | 19 | Validate room profile | 18 | bar: week 2 M to week 2 T
|  | 20 | Create advanced filter options | 15 | bar: week 14 T to week 3 M
|  | 21 | Validate filter options | 20 | bar: week 1 F to week 1 S
|  | 22 | Final completion of room info | 6 | bar: week 2 W to week 2 F
|  | 23 | Create round info page | 6 | bar: week 14 T to week 14 S
|  | 24 | Create Summary page | 6 | bar: week 2 W to week 2 F
|  | 25 | Make and complete help pages | 6 | bar: week 2 W to week 2 S
|  | 26 | Create Database | bar: week 14 T to week 3 S
|  | 27 | Create Database structure | 26 | bar: week 15 W to Week 1 M
|  | 28 | Input data into database | 27 | bar: Week 1 T to week 3 T
|  | 29 | Make and finalise Help pages | 6 | bar: week 2 W to week 2 S
|  | 30 | System Testing
|  | 31 | Documents and reports